## Execution Plan
Phase | Task Description | Start Date | End Date | Status | Notes / Commits
Project Inception & Planning | Requirement gathering and ideation | 2026-03-23 | 2026-03-27 | Completed | Defined scope for SME AutoFlow - AI n8n automation generator.
Project Inception & Planning | Architecture design and technology stack finalization | 2026-03-28 | 2026-03-30 | Completed | Selected FastAPI, Streamlit, ChromaDB, and Gemini API.
Project Setup | Initial repository setup & directory structure | 2026-03-31 | 2026-03-31 | Completed | Initial Commit; Create proper Dir Structure.
Environment Configuration | Setup dependencies, API keys, and environment variables | 2026-04-01 | 2026-04-05 | Completed | Created virtual environments, procured Gemini API keys, setup requirements template.
Data Strategy | Preliminary data assessment & source identification | 2026-04-06 | 2026-04-12 | Completed | Identified n8n templates format, planned preprocessing strategies.
Data Engineering | Data collection, auto-labelling, and dataset builder | 2026-04-13 | 2026-04-14 | Completed | Fetched 1000 raw n8n templates; labeled_dataset.csv (1000 rows, 9 intent categories).
Machine Learning (Phase 1) | EDA & Model training (Intent Classifier & Node Recommender) | 2026-04-14 | 2026-04-15 | Completed | Trained Intent Classifier (TF-IDF + LR) & Node Recommender; EDA notebooks created.
Backend & RAG Development | RAG retriever setup, Gemini generator, FastAPI endpoints | 2026-04-16 | 2026-04-16 | Completed | ChromaDB + MiniLM-L6-v2; FastAPI endpoints /health, /predict, /generate.
Frontend Development | Streamlit UI implementation | 2026-04-16 | 2026-04-16 | Completed | Streamlit UI with sidebar config, 3-col results, node chips, JSON viewer.
Testing & Documentation | Integration tests and Architecture README | 2026-04-17 | 2026-04-17 | Completed | Integration tests for intent classifier and FastAPI backend; Authored comprehensive README.
Scaling & Security | Scale dataset to 5,000 templates, retrain models, security audit | 2026-04-18 | 2026-04-18 | Completed | Scrubbed raw and processed templates to prevent credential leaks; retrained models.
Deployment & Final Polish | Docker integration, cloud deployment configs, UI fixes | 2026-04-18 | 2026-04-19 | Completed | Added Dev Container, fixed Streamlit state bug, deployment URLs to README.